HABITFLOW

Implementation Plan

From zero to deployed PWA  ·  10 Weeks  ·  5 Phases  ·  3 Sprints per Phase

Version 1.0  ·  2025  ·  Aditya

| 5 Phases | 10 Weeks | 48 Tasks | 12 Milestones | 1 Deployment |
| --- | --- | --- | --- | --- |

# 1. Plan Overview

This document is the single execution reference for building HabitFlow from a blank repository to a deployed, production-ready PWA. It translates the PRD, Frontend Guidelines, Tech Stack, Database Schema, and App Flow documents into a concrete, week-by-week build plan with prioritised tasks, sprint milestones, risk mitigations, and quality gates.

| Property | Value |
| --- | --- |
| Total build time | 10 weeks (solo developer pace) |
| Phases | 5 phases — each ends with a deployable milestone |
| Task count | 48 implementation tasks across all phases |
| Priority system | P0 = must ship, P1 = should ship, P2 = nice-to-have, P3 = post-MVP |
| Effort unit | Days of focused work (1 day = ~4 productive hours for a student) |
| Quality gate | Every phase requires passing Definition of Done before Phase N+1 begins |
| Deployment | Antigravity — static PWA deploy at end of Phase 4 |
| Post-MVP | Phase 5 defines features for v1.1 and beyond |
| Stack reference | React 18 + Vite + Tailwind + Dexie + Zustand + Recharts + D3 |

| 📌 NOTE | This plan assumes a single developer working part-time (student schedule). All timeline estimates include buffer. If working full-time, compress phases by 40%. Each phase is independently deployable — you can stop at any phase and have a working product. |
| --- | --- |

# 2. Master Timeline (Gantt)

A 10-week visual timeline. Each row represents one work stream. Filled cells (█) indicate active weeks for that stream.

| Phase | Focus Area | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Project Setup & Scaffold | █ | █ |  |  |  |  |  |  |  |  |
| Phase 1 | DB Layer + Zod Schemas | █ | █ |  |  |  |  |  |  |  |  |
| Phase 1 | Routing + App Shell |  | █ |  |  |  |  |  |  |  |  |
| Phase 2 | Habit Module (full) |  |  | █ | █ |  |  |  |  |  |  |
| Phase 2 | Task Module (full) |  |  | █ | █ |  |  |  |  |  |  |
| Phase 2 | Dashboard + Today View |  |  |  | █ |  |  |  |  |  |  |
| Phase 3 | Analytics (Recharts + D3) |  |  |  |  | █ | █ |  |  |  |  |
| Phase 3 | Gamification (XP + Badges) |  |  |  |  | █ | █ |  |  |  |  |
| Phase 3 | Notifications + Reminders |  |  |  |  |  | █ |  |  |  |  |
| Phase 4 | Onboarding Flow |  |  |  |  |  |  | █ |  |  |  |
| Phase 4 | PWA + Service Worker |  |  |  |  |  |  | █ | █ |  |  |
| Phase 4 | Settings + Data Export/Import |  |  |  |  |  |  | █ | █ |  |  |
| Phase 4 | Testing + Accessibility |  |  |  |  |  |  |  | █ |  |  |
| Phase 4 | Deploy to Antigravity |  |  |  |  |  |  |  |  | █ |  |
| Phase 5 | Post-MVP Features |  |  |  |  |  |  |  |  | █ | █ |

| 📌 NOTE | Phases 1–4 are sequential — each must complete before the next begins. Phase 5 is open-ended and can begin whenever the team has capacity after the v1.0 deploy. |
| --- | --- |

# 3. Phase 1 — Foundation (Weeks 1–2)

🏗️ Phase 1: Foundation Project scaffold, toolchain, database layer, routing, and app shell.

Phase 1 produces a fully running skeleton — no features yet, but every architectural decision is locked in. The end of Phase 1 means: the app loads, routes work, IndexedDB is initialised, all shared components exist as skeletons, and linting + TypeScript are at zero errors.

## 3.1 Sprint 1A — Project Scaffold & Toolchain (Days 1–3)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 1-01 | Initialise Vite + React 18 + TypeScript project with pnpm | P0 | 0.5d | — | Sprint 1A |
| 1-02 | Configure Tailwind CSS v4 + PostCSS + prettier-plugin-tailwindcss | P0 | 0.5d | 1-01 | Sprint 1A |
| 1-03 | Set up ESLint (airbnb-typescript) + Prettier with enforced rules | P0 | 0.5d | 1-01 | Sprint 1A |
| 1-04 | Configure Husky pre-commit hooks (lint + type-check + format) | P0 | 0.5d | 1-03 | Sprint 1A |
| 1-05 | Set up Vitest + React Testing Library + jsdom environment | P0 | 0.5d | 1-01 | Sprint 1A |
| 1-06 | Configure path aliases (@/...) in tsconfig.json + vite.config.ts | P0 | 0.5d | 1-01 | Sprint 1A |
| 1-07 | Install and configure all production dependencies (see Tech Stack doc) | P0 | 1d | 1-01 | Sprint 1A |
| 1-08 | Create folder structure per Frontend Guidelines Section 2 | P0 | 0.5d | 1-01 | Sprint 1A |
| 1-09 | Set up Git repository + initial commit + branch strategy | P0 | 0.5d | — | Sprint 1A |

## 3.2 Sprint 1B — Database Layer (Days 4–7)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 1-10 | Write all Zod schemas (HabitSchema, TaskSchema, etc.) per DB Schema doc | P0 | 1d | 1-08 | Sprint 1B |
| 1-11 | Implement Dexie DB class (HabitFlowDB) with v1 schema + all indexes | P0 | 1d | 1-10 | Sprint 1B |
| 1-12 | Write initDB() singleton initialiser + userXP seed function | P0 | 0.5d | 1-11 | Sprint 1B |
| 1-13 | Write habitService (CRUD: create, update, archive, delete) | P0 | 1d | 1-11 | Sprint 1B |
| 1-14 | Write habitLogService (checkIn upsert, streak calc algorithm) | P0 | 1.5d | 1-13 | Sprint 1B |
| 1-15 | Write taskService (create, complete, delete with subtask cascade) | P0 | 1d | 1-11 | Sprint 1B |
| 1-16 | Write unit tests for streak calculation algorithm (>90% coverage) | P0 | 1d | 1-14 | Sprint 1B |
| 1-17 | Write unit tests for all Zod schemas (valid + invalid inputs) | P0 | 0.5d | 1-10 | Sprint 1B |

## 3.3 Sprint 1C — Routing, Shell & Shared Components (Days 8–14)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 1-18 | Implement React Router v6 with all 18 routes + lazy loading | P0 | 1d | 1-08 | Sprint 1C |
| 1-19 | Build AppShell layout: Sidebar (desktop) + Bottom Tab Bar (mobile) | P0 | 1.5d | 1-18 | Sprint 1C |
| 1-20 | Build ThemeProvider: light/dark/system + CSS variable injection | P0 | 0.5d | 1-02 | Sprint 1C |
| 1-21 | Build shared Button component (4 variants, loading state, icon support) | P0 | 0.5d | 1-02 | Sprint 1C |
| 1-22 | Build shared Input, Textarea, Badge, Skeleton components | P0 | 1d | 1-21 | Sprint 1C |
| 1-23 | Build Modal + Drawer (focus trap, ESC close, backdrop) | P0 | 1d | 1-21 | Sprint 1C |
| 1-24 | Build StatCard, EmptyState, ConfirmDialog shared components | P0 | 0.5d | 1-21 | Sprint 1C |
| 1-25 | Build global Toast system (Zustand store + auto-dismiss) | P0 | 0.5d | 1-21 | Sprint 1C |
| 1-26 | Build Progress ring (SVG) and Progress bar components | P0 | 0.5d | 1-21 | Sprint 1C |
| 1-27 | Set up Zustand stores: useHabitStore, useTaskStore, useUIStore | P0 | 0.5d | 1-08 | Sprint 1C |

## 3.4 Phase 1 — Definition of Done

| ☐ | Definition of Done — Every Task Must Meet All These Before Marking Complete |
| --- | --- |
| ☐ | pnpm dev starts with zero TypeScript errors and zero ESLint warnings |
| ☐ | All 18 routes render their placeholder screens without crashing |
| ☐ | AppShell sidebar and bottom tab bar render correctly at 375px, 768px, 1280px |
| ☐ | Dexie DB initialises on first load (confirmed in browser DevTools → Application → IndexedDB) |
| ☐ | initDB() creates the userXP singleton record |
| ☐ | All Zod schemas pass their unit test suites (>90% coverage) |
| ☐ | Streak algorithm unit tests pass with 100% branch coverage |
| ☐ | Husky pre-commit hook blocks commits with TypeScript errors |
| ☐ | Dark mode toggle works and CSS variables update globally |
| ☐ | All shared components (Button, Input, Modal, Drawer, Toast) render and are keyboard accessible |
| ☐ | pnpm build produces zero errors and output is < 400KB gzipped total |

# 4. Phase 2 — Core Features (Weeks 3–4)

⚙️ Phase 2: Core Features Habit tracking loop + task management + dashboard. The app becomes usable.

Phase 2 delivers the core habit check-in loop and full task management. By the end of Phase 2, a user can create habits, check them off daily, build streaks, create tasks, and see a working dashboard. This is the minimum loveable version.

## 4.1 Sprint 2A — Habit Module (Days 15–20)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 2-01 | Build HabitCard component (all 4 check-in widget types) | P0 | 1.5d | 1-22 | Sprint 2A |
| 2-02 | Build Create/Edit Habit drawer with all conditional fields | P0 | 1.5d | 1-23 | Sprint 2A |
| 2-03 | Build emoji picker integration (emoji-mart) in habit form | P1 | 0.5d | 2-02 | Sprint 2A |
| 2-04 | Build Habits Today view (sortable, filterable, by-category) | P0 | 1d | 2-01 | Sprint 2A |
| 2-05 | Implement check-in logic: optimistic update + DB write + XP award | P0 | 1d | 1-14 | Sprint 2A |
| 2-06 | Build Habit Detail page: stats row, mini 7-day calendar, log list | P0 | 1.5d | 2-01 | Sprint 2A |
| 2-07 | Build streak display (current + best) with flame icon animation | P0 | 0.5d | 1-16 | Sprint 2A |
| 2-08 | Build log entry edit modal (backdate value + note) | P1 | 0.5d | 2-06 | Sprint 2A |
| 2-09 | Implement archive + hard-delete habit flows with confirmation | P0 | 0.5d | 1-13 | Sprint 2A |
| 2-10 | Write component tests for HabitCard (all 4 types, keyboard nav) | P0 | 1d | 2-01 | Sprint 2A |

## 4.2 Sprint 2B — Task Module (Days 21–26)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 2-11 | Build TaskRow component (priority dot, checkbox, due date chip) | P0 | 1d | 1-22 | Sprint 2B |
| 2-12 | Build Task Detail drawer (auto-save, subtasks, status chips) | P0 | 2d | 1-23 | Sprint 2B |
| 2-13 | Build Tasks Inbox view with sort + filter + group-by | P0 | 1d | 2-11 | Sprint 2B |
| 2-14 | Build Tasks Today view with overdue section | P0 | 0.5d | 2-13 | Sprint 2B |
| 2-15 | Build Tasks Upcoming view (14-day grouped + mini calendar strip) | P1 | 1d | 2-13 | Sprint 2B |
| 2-16 | Build Projects view + Create Project drawer | P1 | 1d | 1-23 | Sprint 2B |
| 2-17 | Implement recurring task spawn logic in taskService | P0 | 1d | 1-15 | Sprint 2B |
| 2-18 | Implement subtask cascade delete (recursive) | P0 | 0.5d | 1-15 | Sprint 2B |
| 2-19 | Implement label CRUD + label cleanup transaction | P1 | 0.5d | 1-11 | Sprint 2B |
| 2-20 | Build dnd-kit drag-and-drop for task reordering | P1 | 1d | 2-11 | Sprint 2B |

## 4.3 Sprint 2C — Dashboard (Days 27–28)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 2-21 | Build Dashboard layout: completion ring, habit grid, task strip | P0 | 1.5d | 2-01 | Sprint 2C |
| 2-22 | Build animated SVG completion ring (daily progress) | P0 | 1d | 2-21 | Sprint 2C |
| 2-23 | Build Quick-Add panel (slide-over: habit tab + task tab) | P0 | 1d | 1-23 | Sprint 2C |
| 2-24 | Implement global Q/T keyboard shortcut for Quick-Add | P1 | 0.5d | 2-23 | Sprint 2C |

## 4.4 Phase 2 — Definition of Done

| ☐ | Definition of Done — Every Task Must Meet All These Before Marking Complete |
| --- | --- |
| ☐ | User can create a habit, check it in today, and see streak increment to 1 |
| ☐ | All 4 habit types (boolean, count, duration, rating) work correctly with correct DB writes |
| ☐ | Backdating a habit entry recalculates streak correctly |
| ☐ | User can create a task, set priority and due date, and mark it complete |
| ☐ | Completing a recurring task spawns the next instance with correct dueDate |
| ☐ | Subtask deletion cascades to all children recursively |
| ☐ | Dashboard completion ring animates on load and updates live on check-in |
| ☐ | Quick-Add panel opens on Q key and closes on ESC |
| ☐ | Drag-and-drop task reorder persists sortOrder to DB |
| ☐ | All screens pass mobile layout check at 375px viewport |
| ☐ | No console errors or warnings in production build |
| ☐ | HabitCard and TaskRow component tests pass |

# 5. Phase 3 — Analytics & Gamification (Weeks 5–6)

📊 Phase 3: Analytics & Gamification Heatmaps, charts, XP system, badges, and push notifications.

Phase 3 is where HabitFlow earns its differentiation. The analytics suite and gamification layer are built in full. By the end of Phase 3, the app has a fully functional data visualisation layer and a working XP/badge/level system.

## 5.1 Sprint 3A — Analytics Module (Days 29–36)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 3-01 | Build Analytics Overview page layout + period selector | P0 | 1d | 1-18 | Sprint 3A |
| 3-02 | Build D3.js GitHub-style 52-week heatmap component | P0 | 2d | 1-07 | Sprint 3A |
| 3-03 | Build Recharts line chart (7-day rolling trend per habit) | P0 | 1d | 1-07 | Sprint 3A |
| 3-04 | Build Recharts bar chart (streak history — each bar = 1 streak) | P0 | 1d | 1-07 | Sprint 3A |
| 3-05 | Build Recharts radar chart (weekly habit overview Mon–Sun) | P0 | 1d | 1-07 | Sprint 3A |
| 3-06 | Build Recharts scatter chart (habit-mood correlation) | P1 | 1d | 1-07 | Sprint 3A |
| 3-07 | Build time-of-day histogram (check-in distribution 0–23h) | P1 | 0.5d | 1-07 | Sprint 3A |
| 3-08 | Build Habit Analytics detail page (5-tab layout) | P0 | 1.5d | 3-02 | Sprint 3A |
| 3-09 | Build analytics stats cards (totals, averages, completion %) | P0 | 0.5d | 1-24 | Sprint 3A |
| 3-10 | Build period comparison view (two date range pickers + side-by-side chart) | P2 | 1d | 3-03 | Sprint 3A |
| 3-11 | Implement CSV export (Papa Parse) for habit logs | P1 | 0.5d | 1-11 | Sprint 3A |
| 3-12 | Move heavy analytics calculations to Web Worker | P2 | 1d | 3-02 | Sprint 3A |

## 5.2 Sprint 3B — Gamification (Days 37–40)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 3-13 | Build XP award service (base + streak bonus + milestone bonus) | P1 | 1d | 1-16 | Sprint 3B |
| 3-14 | Build level-up detection + level-up modal (confetti animation) | P1 | 1d | 3-13 | Sprint 3B |
| 3-15 | Build XP counter animation (number roll on award) | P1 | 0.5d | 3-13 | Sprint 3B |
| 3-16 | Implement all 15 badge earn conditions + badge earned modal | P1 | 1.5d | 3-13 | Sprint 3B |
| 3-17 | Build daily score composite calculation (habits + tasks) | P1 | 0.5d | 3-13 | Sprint 3B |
| 3-18 | Build badge grid in Settings (earned / locked states) | P1 | 0.5d | 3-16 | Sprint 3B |

## 5.3 Sprint 3C — Notifications (Days 41–42)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 3-19 | Implement Notification.requestPermission() flow with UI states | P0 | 0.5d | 1-11 | Sprint 3C |
| 3-20 | Register Service Worker + schedule per-habit push notifications | P0 | 1d | 3-19 | Sprint 3C |
| 3-21 | Implement streak-at-risk alert (6pm check for unlogged habits) | P1 | 0.5d | 3-20 | Sprint 3C |
| 3-22 | Implement morning briefing notification (8am daily digest) | P1 | 0.5d | 3-20 | Sprint 3C |

## 5.4 Phase 3 — Definition of Done

| ☐ | Definition of Done — Every Task Must Meet All These Before Marking Complete |
| --- | --- |
| ☐ | Heatmap renders correctly for 52 weeks with colour scale matching completion % |
| ☐ | Heatmap cells are keyboard accessible (Tab to navigate, Enter to open log entry) |
| ☐ | All 5 Recharts chart types render with correct data and CSS variable colours |
| ☐ | Charts respect prefers-reduced-motion (isAnimationActive=false when reduced) |
| ☐ | Completing a habit awards correct XP and updates the userXP singleton in DB |
| ☐ | Level-up modal triggers when XP crosses level threshold |
| ☐ | All 15 badge conditions are tested and trigger correctly |
| ☐ | Browser push notification appears at scheduled reminder time |
| ☐ | Notification permission denied state shows correct fallback UI in Settings |
| ☐ | Analytics period selector updates all charts simultaneously |
| ☐ | CSV export downloads a valid file with correct habit log data |
| ☐ | All chart containers have role='img' and aria-label with text summary |

# 6. Phase 4 — Polish, PWA & Deploy (Weeks 7–9)

🚀 Phase 4: Polish, PWA & Deploy Onboarding, settings, accessibility, testing, and Antigravity deployment.

Phase 4 takes the working feature set and makes it production-ready. Onboarding flow, full settings, data export/import, PWA manifest, Service Worker, accessibility audit, and deployment to Antigravity.

## 6.1 Sprint 4A — Onboarding & Settings (Days 43–49)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 4-01 | Build Onboarding Welcome screen (hero, value prop, Get Started CTA) | P0 | 0.5d | 1-18 | Sprint 4A |
| 4-02 | Build Onboarding Habit Picker (template grid, multi-select, search) | P0 | 1d | 4-01 | Sprint 4A |
| 4-03 | Build Onboarding Reminder Setup (permission flow + time picker) | P0 | 0.5d | 3-19 | Sprint 4A |
| 4-04 | Build Onboarding Theme Picker (live preview, dark/light/system) | P0 | 0.5d | 1-20 | Sprint 4A |
| 4-05 | Implement first-run flag check + onboarding routing guard | P0 | 0.5d | 1-18 | Sprint 4A |
| 4-06 | Build Settings hub page (all 6 sections per App Flow doc) | P0 | 1.5d | 1-18 | Sprint 4A |
| 4-07 | Implement JSON full-data export (all 8 collections) | P0 | 1d | 1-11 | Sprint 4A |
| 4-08 | Implement JSON import (Zod validate → confirm modal → bulk insert) | P0 | 1d | 4-07 | Sprint 4A |
| 4-09 | Implement Reset All Data flow (typed confirmation + transaction clear) | P0 | 0.5d | 1-11 | Sprint 4A |
| 4-10 | Build storage usage estimation display in Settings | P1 | 0.5d | 1-11 | Sprint 4A |

## 6.2 Sprint 4B — PWA & Performance (Days 50–56)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 4-11 | Configure vite-plugin-pwa: manifest, icons (192 + 512px), theme colour | P0 | 0.5d | 1-01 | Sprint 4B |
| 4-12 | Configure Workbox for asset precaching + runtime caching strategy | P0 | 1d | 4-11 | Sprint 4B |
| 4-13 | Generate VAPID keys and configure Web Push integration | P1 | 0.5d | 3-20 | Sprint 4B |
| 4-14 | Test PWA install flow on Chrome (desktop) + Safari (iOS) + Chrome (Android) | P0 | 0.5d | 4-11 | Sprint 4B |
| 4-15 | Run Lighthouse audit — hit all Core Web Vitals targets (LCP<1.5s, CLS<0.05) | P0 | 1d | 4-12 | Sprint 4B |
| 4-16 | Implement route-level code splitting (verify chunks in pnpm analyze) | P0 | 0.5d | 1-18 | Sprint 4B |
| 4-17 | Add React Error Boundaries around every route and every chart | P0 | 0.5d | 1-18 | Sprint 4B |
| 4-18 | Build all empty states (habits, tasks, analytics) per App Flow doc | P0 | 1d | 1-24 | Sprint 4B |
| 4-19 | Build Command Palette (/ shortcut, fuzzy search habits + tasks) | P2 | 1d | 1-25 | Sprint 4B |

## 6.3 Sprint 4C — Accessibility, Testing & Deploy (Days 57–63)

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 4-20 | Full keyboard navigation audit — all interactive elements reachable by Tab | P0 | 1d | All Phase 4 | Sprint 4C |
| 4-21 | Add ARIA labels to all icon buttons, progress rings, chart containers | P0 | 1d | 4-20 | Sprint 4C |
| 4-22 | Test with VoiceOver (macOS) + NVDA (Windows) — fix critical a11y issues | P0 | 1d | 4-21 | Sprint 4C |
| 4-23 | Write Playwright E2E tests for 3 critical flows: check-in, task-complete, analytics-load | P0 | 1.5d | 4-17 | Sprint 4C |
| 4-24 | Fix all bugs found during E2E and accessibility testing | P0 | 1d | 4-23 | Sprint 4C |
| 4-25 | Configure Antigravity deployment (SPA redirect rule + env vars) | P0 | 0.5d | 4-12 | Sprint 4C |
| 4-26 | First production deploy to Antigravity — smoke test all flows | P0 | 0.5d | 4-25 | Sprint 4C |
| 4-27 | Post-deploy: run Lighthouse on live URL, verify PWA install works | P0 | 0.5d | 4-26 | Sprint 4C |

## 6.4 Phase 4 — Definition of Done (Launch Criteria)

| ☐ | Definition of Done — Every Task Must Meet All These Before Marking Complete |
| --- | --- |
| ☐ | Onboarding flow runs on first load, seeds selected habits, sets hasOnboarded flag |
| ☐ | JSON export produces a valid .habitflow.json file restoreable via Import |
| ☐ | Import correctly validates, previews, and bulk-inserts data into all 8 collections |
| ☐ | Reset All Data clears all 8 collections in a single transaction and reloads to onboarding |
| ☐ | PWA installs on Chrome desktop and appears in Applications list |
| ☐ | Service Worker precaches all static assets — confirmed via Workbox devtools panel |
| ☐ | Lighthouse PWA score > 90 on live Antigravity URL |
| ☐ | All Core Web Vitals pass: LCP < 1.5s, CLS < 0.05, INP < 100ms |
| ☐ | Initial JS bundle < 200KB gzipped (verified via pnpm analyze) |
| ☐ | All screens pass WCAG 2.1 AA colour contrast (>4.5:1 for body text) |
| ☐ | All 3 Playwright E2E tests pass on Chromium, Firefox, and WebKit |
| ☐ | App is fully functional with Chrome DevTools → Network → Offline checked |
| ☐ | Zero console errors on the live deployed URL |
| ☐ | App URL shared, tested on a real mobile device |

# 7. Phase 5 — Post-MVP Features (Weeks 9–10+)

🔮 Phase 5: Post-MVP Features that enhance v1.0 after launch. Sequenced by value.

Phase 5 begins after the v1.0 deploy to Antigravity. These features are sequenced by user value and implementation complexity. Each can be built and deployed independently as patch releases.

| ID | Task | Pri | Effort | Depends On | Phase |
| --- | --- | --- | --- | --- | --- |
| 5-01 | Natural language date parsing (chrono-node) in Quick-Add title field | P1 | 1d | 4-08 | Phase 5 |
| 5-02 | Eisenhower Matrix view for tasks (2×2 urgent/important quadrant) | P2 | 1d | 2-13 | Phase 5 |
| 5-03 | Task dependency graph (blocked-by relationships between tasks) | P2 | 2d | 2-12 | Phase 5 |
| 5-04 | Habit correlation viewer (side-by-side heatmap comparison) | P2 | 1d | 3-02 | Phase 5 |
| 5-05 | Mood log UI improvements (energy slider, richer emotion picker) | P2 | 1d | 1-11 | Phase 5 |
| 5-06 | Weekly review auto-generated summary (Sunday 7pm) | P2 | 1d | 3-09 | Phase 5 |
| 5-07 | Streak freeze tokens (limited per month, prevents streak break) | P2 | 1d | 1-16 | Phase 5 |
| 5-08 | Habit templates library (30+ pre-built habit packs by category) | P2 | 1d | 2-02 | Phase 5 |
| 5-09 | Optional Supabase cloud sync (auth + realtime + last-write-wins) | P3 | 5d | 4-07 | Phase 5 |
| 5-10 | Ollama local LLM habit suggestions (based on goal text input) | P3 | 3d | All Phase 5 | Phase 5 |
| 5-11 | Capacitor wrapper for native iOS/Android PWA deployment | P3 | 3d | 4-11 | Phase 5 |

# 8. Sprint Structure & Ceremonies

Each phase is divided into sprints of 7 working days. Given solo development, ceremonies are lightweight — the goal is structure without overhead.

| Sprint | Duration | Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| Day 1 | Sprint kickoff | • Review tasks for the sprint • Re-read relevant doc sections • Set up feature branches | All tasks understood, branches created |
| Days 2-6 | Build | • One task per half-day minimum • Commit at end of each session • Zero WIP tasks by Day 5 | Every task has a commit. Feature branches merged to main. |
| Day 7 | Sprint close | • Code review (self) • Lighthouse audit if applicable • DoD checklist • Update this doc with actuals | DoD checklist passes. Milestone deployed to preview. |

| 📐 RULE | Never carry unfinished tasks from one sprint to the next without explicitly demoting their priority. A task that can't fit in the sprint is either descoped to Phase 5 or split into smaller subtasks. |
| --- | --- |

# 9. Risk Register

Pre-identified risks with impact, probability, and mitigation strategy. Review this list at the start of each phase.

| # | Risk | Impact | Prob. | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | D3.js heatmap takes longer than 2 days — complex SVG geometry + React integration | High | Medium | Timebox to 2 days. If blocked: ship Recharts CalendarChart as temporary fallback. Heatmap is P0 but a basic version is acceptable for v1.0. |
| R2 | IndexedDB storage cleared by browser (Safari ITP, private mode) | High | Low | Call navigator.storage.persist() on first load. Show warning banner if denied. Prompt weekly JSON export as a habit. |
| R3 | Notification permission rejected by user — core reminder feature unusable | Medium | Medium | Design full in-app fallback: visual reminders on dashboard if push unavailable. Remind users to re-enable in onboarding. |
| R4 | Antigravity SPA routing issue — 404 on direct URL access | Medium | Low | Add catch-all redirect rule in Antigravity config on Day 1 of deploy sprint. Test all 18 routes directly. |
| R5 | framer-motion bundle size exceeds performance budget | Medium | Low | Import only used exports. If budget exceeded: replace with CSS transitions for non-critical animations. Monitor with pnpm analyze after every phase. |
| R6 | Dexie migration breaks existing data during development | High | Medium | Follow the strict migration rule: never edit previous version() blocks. Test migrations with a seeded DB before deploying each phase. |
| R7 | Playwright E2E tests flake on CI due to timing issues | Low | Medium | Add explicit waitFor assertions. Never rely on arbitrary timeouts. Use data-testid attributes consistently. |
| R8 | Scope creep — temptation to add Phase 5 features before Phase 4 is complete | Medium | High | Hard rule: no new features until DoD checklist passes for current phase. Use this document as the authority. |
| R9 | dnd-kit drag-and-drop breaks on mobile touch — gesture conflicts | Medium | Medium | Test dnd-kit on real iOS/Android device at end of Sprint 2B. If broken: use long-press delay setting in dnd-kit config. |
| R10 | Web Worker for analytics fails in some browsers (Safari 15) | Low | Low | Wrap in try/catch with graceful fallback to main thread calculation. Heavy calcs only: heatmap + correlation chart. |

# 10. Quality Gates & Success Metrics

## 10.1 Per-Phase Technical Gates

| Gate | Measurement | Tool |
| --- | --- | --- |
| TypeScript strict | Zero tsc --noEmit errors | tsc |
| Lint clean | Zero ESLint errors, zero warnings | eslint --max-warnings 0 |
| Test coverage | >80% statements, >70% branches | vitest --coverage |
| Bundle budget | Initial JS < 200KB gzipped | vite-bundle-visualizer |
| Lighthouse PWA | >90 PWA score on deployed URL | Lighthouse CI |
| Core Web Vitals | LCP<1.5s, CLS<0.05, INP<100ms | Lighthouse / CrUX |
| A11y contrast | >4.5:1 ratio for all body text | axe-core / Colour Contrast Analyser |
| E2E tests | All 3 critical flows pass on 3 browsers | Playwright |
| Offline test | Full feature parity with Network: Offline | Chrome DevTools |

## 10.2 Progressive Quality Metrics (by Phase)

| Metric | Phase 1 Target | Phase 2 Target | Phase 3 Target | Tool |
| --- | --- | --- | --- | --- |
| TypeScript errors | 0 | 0 | 0 | tsc |
| ESLint warnings | 0 | 0 | 0 | eslint |
| Unit test coverage | >80% | >82% | >85% | vitest |
| Lighthouse performance | — | >70 | >85 | Lighthouse |
| Bundle size (initial) | <300KB | <250KB | <200KB | rollup-visualizer |
| Streak calc accuracy | 100% unit | 100% unit | 100%+E2E | vitest + playwright |
| Screens with a11y | 50% | 80% | 100% | axe-core |
| Mobile viewport pass | Phase 1 | All screens | All+E2E | manual + playwright |
| DB migration tests | v1 tested | v2 tested | v1-v5 all | vitest |

# 11. Daily Development Workflow

| 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- |
| Plan | Branch | Build | Commit | Review | Merge |
| Review today's tasks from this doc. Read relevant code from yesterday. | git checkout -b feat/task-id-short-description | Write tests first if logic-heavy. Build feature. Run tests. | Conventional commit message. Husky checks pass. | Self-review diff. Check mobile at 375px. Run pnpm build. | Merge to main. Delete branch. Update task status. |

## 11.1 File Creation Order (Per Feature)

- Types: add to features/{name}/types.ts

- Zod schema: update db/schemas.ts if new DB entity

- Service: write features/{name}/services/{name}Service.ts with unit tests

- Hook: write features/{name}/hooks/use{Name}.ts

- Store: update features/{name}/stores/{name}Store.ts

- Component: write features/{name}/components/{Name}.tsx with colocated test

- Route page: update features/{name}/{Name}Page.tsx

- Router: add route to app/Router.tsx

## 11.2 Commit Message Quick Reference

Shell

# Format: type(scope): description feat(habits): add grace day toggle to habit form feat(tasks): implement recurring task spawn on complete feat(analytics): build D3 heatmap component feat(gamification): add level-up modal with confetti fix(streak): correct off-by-one in weekly schedule calc fix(tasks): prevent subtask cascade from missing nested children ui(dashboard): fix completion ring gap on Safari ui(mobile): correct bottom tab z-index on iOS perf(analytics): move heatmap calculation to Web Worker test(habits): add HabitCard keyboard interaction tests a11y(tasks): add aria-label to priority dot buttons chore(deps): upgrade dexie to 4.1.0 docs: update implementation plan with Phase 2 actuals

# 12. First-Day Setup Checklist

Run this checklist exactly once, in order, before writing any feature code.

| ☐ | Definition of Done — Every Task Must Meet All These Before Marking Complete |
| --- | --- |
| ☐ | Node.js 22 LTS installed (verify: node --version shows v22.x.x) |
| ☐ | pnpm 9 installed globally (verify: pnpm --version shows 9.x.x) |
| ☐ | VS Code installed with all 7 recommended extensions (see Tech Stack doc §15.2) |
| ☐ | pnpm create vite@latest habitflow -- --template react-ts executed |
| ☐ | cd habitflow && pnpm install executed |
| ☐ | All production + dev dependencies from Tech Stack doc §13 installed |
| ☐ | Tailwind CSS v4 + PostCSS configured and producing output (verify a class renders) |
| ☐ | Folder structure from Frontend Guidelines §2 created (all 20+ folders) |
| ☐ | tsconfig.json strict mode enabled with all required options |
| ☐ | ESLint configured (airbnb-typescript) — pnpm lint passes on empty project |
| ☐ | Prettier + prettier-plugin-tailwindcss configured — pnpm format runs |
| ☐ | Husky installed — git commit triggers pre-commit hook |
| ☐ | Vitest configured — pnpm test finds and runs a placeholder test |
| ☐ | Dexie installed — db.ts skeleton created and DB initialises in browser DevTools |
| ☐ | React Router configured — pnpm dev shows placeholder text at / without errors |
| ☐ | Git repo initialised — first commit pushed to remote |

# 13. Document Cross-Reference

Every implementation decision in this plan references a specific section of the 5 HabitFlow documents. Use this table when you need more detail on any task.

| If you need... | Read this document | Specific section |
| --- | --- | --- |
| Feature requirements | PRD | Section 4 — Core Feature Set |
| Component structure | Frontend Guidelines | Section 4 — Component Architecture |
| TypeScript patterns | Frontend Guidelines | Section 5 — TypeScript Standards |
| Tailwind class order | Frontend Guidelines | Section 6 — Tailwind Conventions |
| State management pattern | Frontend Guidelines | Section 7 — State Management |
| Animation specs | Frontend Guidelines | Section 8 — Animation & Motion |
| Accessibility requirements | Frontend Guidelines | Section 9 — Accessibility |
| Performance budgets | Frontend Guidelines | Section 10 — Performance |
| Chart library assignment | Tech Stack | Section 5 — Charts & Visualisation |
| NPM package versions | Tech Stack | Section 13 — Dependency Map |
| Architecture decisions | Tech Stack | Section 14 — Decision Log |
| DB schema / field specs | DB Schema | Section 3 — Collection Schemas |
| Zod schema code | DB Schema | Section 4 — Zod Validation Schemas |
| Dexie implementation | DB Schema | Section 5 — Dexie.js Implementation |
| Service layer patterns | DB Schema | Section 6 — Service Layer |
| Migration strategy | DB Schema | Section 7 — Migration Strategy |
| Screen specs / UI elements | App Flow | Section 3–9 — Individual Flow Sections |
| Navigation routes | App Flow | Section 2.2 — Navigation Map |
| Edge cases | App Flow | Section 11 — Edge Cases & Error Flows |
| Keyboard shortcuts | App Flow | Section 12 — Keyboard & Gesture Map |
| Loading states | App Flow | Section 13 — Loading & Transition States |

# 14. The Golden Rule

Ship a working version at the end of every phase. A deployed, working Phase 1 is worth more than a perfect, un-deployed Phase 4. When in doubt: descope, simplify, ship.

| 📋 Start with this doc Read Section 1 + your current Phase section before every session | ⚡ When stuck > 1 hour Descope the hard part. Ship the 80%. Revisit in Phase 5. | 📊 Before every commit Run: pnpm build && pnpm test. If it fails, don't commit. |
| --- | --- | --- |

End of Implementation Plan  ·  HabitFlow v1.0  ·  Aditya  ·  ZCOER SE AIML